## Road Map
Before meeting with instuctor, complete the blue items | [6 empty] | On Target
Behind Target
Risk of completing on time
Complete
[5 empty] | December | [12 empty] | January
[5 empty] | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W
Objective | Roles | Module Section | Role Owner | Comments | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Status
First Segment: Sketch It Out: 19% |  |  |  | Decide on your overall project, select your question, and build a simple model. You'll connect the model to a fabricated database, using comma-separated values (CSV) or JavaScript Object Notation (JSON) files, to prototype your idea.
Project Kick-off
Proposed Question: |  |  | Becky | Decide on a topic for the project—think of a question that can be answered using data.
Define Dataset |  |  | Becky
Decide on a topic |  | 20.1.1 | Becky | Decide on a topic for the project—think of a question that can be answered using data.
Create Repository |  | 20.1.1 | Aly | Create a repository for the project and invite the other team members to join. Create a repository and establish individual branches for each team member.
Database Diagram |  |  | Becky | If you use a SQL database, you must provide your Entity Relationship Diagram (ERD) with relationships.
Source a dataset (min 1000 data points) |  | 20.1.1 |  | Source a dataset that will suit your needs (you can even use multiple datasets if applicable).
Begin to clean, organize, and perform exploratory data analysis on your datasets so that they're ready for analysis. |  | 20.1.1 |  | Completing an exploratory data analysis will help you determine if your topic is viable or if further consideration (or even a different topic) is needed. It'll also help you prepare for that conversation with your instructor. It's a good idea to think about what metrics you'll be including in the machine learning portion.
Include mockups of a machine learning model and a database. |  | 20.1.1 | Matt
Plan your schedule |  | 20.1.1 | Matt | Project weeks can be intense. Make sure to pad your tasks with extra time. There's an excellent chance you'll find yourself researching issues you've not encountered before, or that you'll want your code to do something more advanced than what has been covered in class. That's all OK!
mockup of a database with sample data |  |  | Becky | Just as you did for the machine learning model, you'll create a mockup or "dummy" database during the first segment of your project to make sure the model works. This mockup will follow the format of the expected database, but it will be simpler and likely in a CSV or JSON format.
Creation of S3 and Postgress Database (AWS) |  |  | Aly | Initial Load of Sample Data
mockup of a machine learning model |  |  | Matt | create a model mockup, importing data in the desired format and exporting data in the required format.
Statistical Analysis (Optional) |  |  |  | If statistical analysis is not included as part of the current analysis, the team should add a description of how it would be included in the next phases of the project | December M: Optional
Decide which technologies will be used |  |  | Group
First Segment Grading |  | 20.1.3
Presentation (30 points) |  | 20.1.3 |  | The team members have drafted their project, including the following: Selected topic Reason they selected the topic Description of the source of data Questions they hope to answer with the data The content does not yet need to be in the form of a presentation. It can be text in the README.md.
GitHub Repository (10 points) |  | 20.1.3 |  | Main Branch The main branch should include: README.md README.md The README.md should include: Description of the communication protocols Individual Branches Requirements for the individual branches follow: At least one branch for each team member Each team member has at least four commits for the duration of the first segment
Machine Learning Model (35 points) |  | 20.1.3 |  | Team members will be expected to present a provisional machine learning model that stands in for the final machine learning model and accomplishes the following: Takes in data from the provisional database Outputs label for input data
Database Integration (25 points) |  | 20.1.3 |  | Team members will be expected to present a provisional database that stands in for the final database and accomplishes the following: First, make sure the database is integrated fully and that it interfaces with the project in some form. For example, does web scraping add or update data? The same thought can be applied to the application programming interface (API) calls as well. Next, there should be at least two tables (or collections if Mongo is being used) in the database. If you're collecting data on plants and their common locations, for example, you would have a table for the plant's information (genus, species, brief description) and a second table for geographic locations. Additionally, there should be at least one join completed within the database. Using the same example from earlier, the two tables could be joined to show all of the plants' information and the locations. Finally, there will need to be at least one connection string included. For example, if you're using PyMongo, you'll need to include a connection string in Python that demonstrates the link between your code and the database. Sample data that mimics the expected final database structure or schema Draft machine learning model is connected to the provisional database
Dashboard (0 points) |  | 20.1.3 |  | There are no deliverables associated with the dashboard for this segment.
Second Segment: Build the Pieces: 19% |  |  |  | Train your model and build out the database you'll use for your final presentation.
Overview |  | 20.2.1 |  | This part of the project cycle is pretty high stakes—the machine learning model needs to grow from "mockup" to "functioning," and the database needs to evolve from "fabricated" to "integrated." There is a lot going on! Remember to take time to breathe. It's okay if you feel stressed, but do something productive about it. Talk it out with your team members or consult your instructor.
Machine learning model | Square | 20.2.5 |  | This means moving from a preliminary model into your machine learning model. During the second segment, the square will focus on the machine learning model. Building off of the preliminary model built in the first segment, continue to refine, train, and test the model. Make sure to document how it ties into the project. There needs to be a description of the model as well as any preprocessing that was involved. Additionally, capture an interpretation of how accurate, precise, or sensitive the model is. One question: If you had more time, where would you like to investigate for finer tuning? Keep this in mind as the presentation is being put together since it could be a really strong talking point. For this segment, continue using the same branch that was created during the last segment. If that branch has already been merged in, that's OK. You can just create a new one to work from instead. There are several questions to keep in mind as you work through this segment: How does it work? Why this specific model? What is the model's accuracy? If there are statistics involved, what stats are being included in analysis and why? If no statistics are involved, what would you include if you had more time? There's a chance you'll run into stumbling blocks here or there, too. Remind yourself that it's OK and not to get stuck—instead of spending vast amounts of time stuck on a single problem, document it, then (during the presentation) discuss how you would approach it differently if you had more time. At the end of this segment, you will need to have a description of the model and a discussion about any preprocessing involved. Additionally, an interpretation of the accuracy, precision, and sensitivity of the model should be included with the submission. Refine the machine learning model you'll be using (train and test).
Database Integration | Triangle | 20.2.6 |  | mockup database created last week will need to be integrated and refined as well, and the visuals that help tell the data story will need to be created. Transform the mockup database into a full database that integrates with your work.
Continue with analysis | Circle | 20.2.7 |  | Continue with analysis and create visuals to accompany the data story. The team member in the circle role will continue to refine the analysis. This includes generating at least three images to use in the presentation and with the dashboard. Imagine that the presentation, and the dashboard, are being shown to a potential employer. Not only do the images need to be neat and clean, but they also need to clearly add weight to the data story being told. A good way to increase the quality of your images is to incorporate a visualization library, such as Seaborn if you're using Python, to make high-quality PNGs that can be reused as needed. Create a new GitHub branch to work from during this segment. This is a great way to get feedback from your team on the visuals you create—they will be able to see them and provide feedback (and encouragement!) as you create them and experiment with different color themes. It's important to keep in mind that the dashboard will require interactivity; so if you're creating maps using GeoJSON, this is a great time to make sure some fancy things are included, such as layers and filters.
GitHub's peer review tools | Team | 20.2.4 |  | You'll merge in your separate branches and create new ones for this segment's tasks. This means dipping your toe into the world of completing peer reviews and pull requests (PRs). Remember, communication is key. When it comes to GitHub, commenting on peer reviews is another avenue for communication. Remember, feedback is constructive. Thoughtfully discuss and patiently consider differing opinions. By doing so, we can create an even sturdier product. During this segment, you will continue to work together to coax a story from your data. Perform more than one analysis on your data during this segment—analyses that help bring together the larger picture and lend strength to the story. Also, this is a great time to really dive into GitHub. The branches originally created for each person should be merged into the main branch, and new branches are created for each task. Let's take a look at the following flow chart: The flow chart demonstrates the peer review steps: First create a PR. Next, peers will review and then update that PR based on comments. Lastly, the PR is merged into the main branch. When a PR is created, it compares the branch you've been working on to the main branch of the repository. This provides a way for your peers to review the code and/or documentation before merging it into the main branch. Remember, the main branch is the production branch, so everything added to it must be in working order. IMPORTANT Supplemental information on how to create a PR, review the content, and merge the branch can be found in the following document. Download the GitHub Reference Guide (Links to an external site.) GitHub: Merge PRs Let's walk through a scenario. There should be multiple analyses being performed on the data, and each different analysis needs its own branch. Let's say the team member in the triangle role has completed the analysis and opened a PR. Now the PR is available for peer review. In this case, the one in the circle role will check out the branch using git checkout branchname to download the new code onto the computer. Now that the code is local, the one in the circle role can use his or her own tools to run the code. By doing so, the code is checked for any errors. This is also the perfect opportunity to check for spelling mistakes and to ensure the code meets coding guidelines. Once the code in the PR has passed the peer review, it can be merged into the main branch. When a PR is created, it compares the branch you've been working on to the main branch of the repository. This provides a way for your peers to review the code and/or documentation before merging it into the main branch. Remember, the main branch is the production branch, so everything added to it must be in working order.
Analysis and create visuals to accompany the data story | Circle | 20.2.7 |  | Finally, creating an outline for the final dashboard is a good idea as well. A storyboard capturing the main visualizations and other aspects of the dashboard will help smooth out the creation process when it comes time to put everything together. The team member in the circle role will continue to refine the analysis. This includes generating at least three images to use in the presentation and with the dashboard. Imagine that the presentation, and the dashboard, are being shown to a potential employer. Not only do the images need to be neat and clean, but they also need to clearly add weight to the data story being told. A good way to increase the quality of your images is to incorporate a visualization library, such as Seaborn if you're using Python, to make high-quality PNGs that can be reused as needed. Create a new GitHub branch to work from during this segment. This is a great way to get feedback from your team on the visuals you create—they will be able to see them and provide feedback (and encouragement!) as you create them and experiment with different color themes. It's important to keep in mind that the dashboard will require interactivity; so if you're creating maps using GeoJSON, this is a great time to make sure some fancy things are included, such as layers and filters. Continue with analysis and create visuals to accompany the data story.
Dashboard | X | 20.2.8 |  | Outline and begin work on a dashboard to house your final project. Check and test the work completed against the rubric. The team member in the X role will focus on the team's dashboard. Create a storyboard of a dashboard that will be used to display your data findings. Imagine that you and your team will be presenting this dashboard to a potential employer. A potential employer may not be familiar with the dataset you've been working with. Or they may not have seen the specific technology you've used to create the dashboard first-hand. Even if they have, you want to create a dashboard that is easy to understand for everyone. It will also need to include interaction—something more sophisticated than a tooltip. A map with multiple layers, for example, is a powerful tool. Or an interactive chart that can be filtered or has adjustable zoom can lend great strength to analysis. This is something to keep in mind and collaborate on with whomever is in the circle role during this segment.
Presentation (Drafted on Google Slides) |  |  |  | The presentation outlines the project, including the following: Selected topic Reason topic was selected Description of the source of data Questions the team hopes to answer with the data Description of the data exploration phase of the project Description of the analysis phase of the project Slides Presentations are drafted in Google Slides.
Second Segment Grading
Presentation (15 points) |  | 20.2.3 |  | The presentation outlines the project, including the following: Selected topic Reason topic was selected Description of the source of data Questions the team hopes to answer with the data Description of the data exploration phase of the project Description of the analysis phase of the project Slides Presentations are drafted in Google Slides.
GitHub Repository Main Branch (10 points) |  | 20.2.3 |  | Main Branch All code in the main branch is production-ready. The main branch should include: All code necessary to perform exploratory analysis Some code necessary to complete the machine learning portion of project
Github - Read Me |  | 20.2.3 |  | README.md README.md should include: Description of the communication protocols Outline of the project (this may include images, but they should be easy to follow and digest)
Github - Individual Branches |  | 20.2.3 |  | Individual Branches Requirements for the individual branches follow: At least one branch for each team member Each team member has at least four commits for the duration of the second segment (eight total commits per person)
Machine Learning Model (30 points) |  | 20.2.3 |  | The team members are expected to submit the code for the machine learning model, as well as the following: Description of preliminary data preprocessing Description of preliminary feature engineering and preliminary feature selection, including the decision-making process Description of how data was split into training and testing sets Explanation of model choice, including limitations and benefits
Database Integration (30 points) |  | 20.2.3 |  | The team members are expected to present a fully integrated database, including the following: Database stores static data for use during the project Database interfaces with the project in some format (e.g., scraping updates the database) Includes at least two tables (or collections, if using MongoDB) Includes at least one join using the database language (not including any joins in Pandas) Includes at least one connection string (using SQLAlchemy or PyMongo)
Dashboard (15 points) - Google Slides |  | 20.2.3 |  | A blueprint for the dashboard is created and includes all of the following: Storyboard on a Google Slide(s) Description of the tool(s) that will be used to create the final dashboard Description of interactive element(s)
Third Segment: Plug It In: 19% |  |  |  | Connect your final database to your model, continue to train your model, and create your dashboard and presentation.
Machine Learning Model |  |  |  | In your second and third segments, you'll train your model and confirm it's working with your robust database.
Dashboard |  |  |  | You'll demonstrate your dashboard during the presentation, but it is important enough to count as its own aspect of the deliverable. When building your dashboard, keep the following requirements in mind: The dashboard presents a data story that is logical and easy to follow for someone unfamiliar with the topic. It should include all of the following: Images from the initial analysis Data (images or report) from the machine learning task At least one interactive element Either the dashboard is published or the submission includes a screen capture video of it in action.
Fourth Segment: Put It All Together: 40% |  |  |  | Put the final touches on your model, database, and dashboard. Lastly, create and deliver your final presentation to your class.
Machine Learning Model |  |  |  | For the final segment, you'll submit your machine learning model, the description and working code, as well as the following information: Description of data preprocessing Description of feature engineering and the feature selection, including the team's decision-making process Description of how data was split into training and testing sets Explanation of model choice, including limitations and benefits Explanation of changes in model choice (if changes occurred between the Segment 2 and Segment 3 deliverables) Description of how the model was trained (or retrained if the team used an existing model) Description and explanation of model's confusion matrix, including final accuracy score Additionally, the model obviously addresses the question or problem the team is solving.
Dashboard |  |  |  | You'll demonstrate your dashboard during the presentation, but it is important enough to count as its own aspect of the deliverable. When building your dashboard, keep the following requirements in mind: The dashboard presents a data story that is logical and easy to follow for someone unfamiliar with the topic. It should include all of the following: Images from the initial analysis Data (images or report) from the machine learning task At least one interactive element Either the dashboard is published or the submission includes a screen capture video of it in action.
Go-Live
Individual Self-Assessment: 3%
Square |  | 20.1.5 | Aly | The team member in the square role will be responsible for the repository.
Triangle |  | 20.1.6 | Matt | The member in the triangle role will create a mockup of a machine learning model. This can even be a diagram that explains how it will work concurrently with the rest of the project steps. Keep the following questions in mind as the machine learning model is developed: Which model did you choose and why? How are you training your model? What is the model's accuracy? How does this model work?
Circle |  |  | Becky | The member in the circle role will create a mockup of a database with a set of sample data, or even fabricated data. This will ensure the database will work seamlessly with the rest of the project.
X (Optional for teams of 3) |  |  | Group | The member in the X role will decide which technologies will be used for each step of the project.

## Triangle
The team member in the triangle role is responsible for creating a simple machine learning model. Creating a simple model this early in the design process helps a team better understand where and how a machine learning model will fit into the project. This also grants more time to work out the specifics related to machine learning.
Keep the following questions in mind as the machine learning model is developed:
Which model did you choose and why?
How are you training your model?
What is the model's accuracy?
How does this model work?
The first segment is all about preparation, so a simple model will cover the first question—the type of machine learning model chosen and why. To get started, create a simple model that isn't concerned with accuracy. Basically, you want your model to take input data and return a label—and that's it!
Submitting a link to a repository branch is very similar to submitting a link to your repository. From the project repository's main page, click the "branches" link:
From there, the next window shows all of the active branches for the repository. Click on the name of your new branch:
The next page looks exactly like the main page for the repository—the only difference is that it's also displaying the file you added. You'll submit the link in the address bar: